{"text_format":"3","workbook":"xlsx","n_sheets":13,"sheets":["A_1 招标工程量清单封面","B_1 招标工程量清单扉页","C 招标说明","1.2 E.1 分部分项工程量清单计价表","3.1 E.1 分部分项工程量清单计价表(所有标题)","3.2 附录F 措施项目清单计价表","3.3 附录G 不可竞争项目清单与计价表","4.1 E.1 分部分项工程量清单计价表(所有标题)","4.2 附录F 措施项目清单计价表","4.3 附录G 不可竞争项目清单与计价表","5.1 E.1 分部分项工程量清单计价表(所有标题)","5.2 附录F 措施项目清单计价表","5.3 附录G 不可竞争项目清单与计价表"],"not_rendered":{"defined_names":10},"read":"whole","date_system":"1900"}

{"sheet":"A_1 招标工程量清单封面","index":0,"n_rows":10,"n_cols":7,"rows_kept":10,"merged":[[0,1,0,5],[1,0,1,6],[2,2,2,6],[3,1,3,2],[3,5,3,6],[4,1,4,5],[5,1,5,5],[6,1,6,5],[7,1,7,5],[8,1,8,5],[9,0,9,6]]}
[null,"海淀区翠微中里16号楼改造",{"$nulls":4},"工程"]
["招标工程量清单"]
[]
[]
["招  标  人:"]
[null,"\n(单位盖章)"]
["造价咨询人:"]
[null,"\n(单位盖章)"]
[]
["安徽省建设工程造价计价软件测评合格编号2018JS-06"]

{"sheet":"B_1 招标工程量清单扉页","index":1,"n_rows":12,"n_cols":7,"rows_kept":12,"merged":[[0,1,0,5],[2,0,2,6],[4,1,4,2],[4,5,4,6],[5,1,5,2],[5,5,5,6],[6,1,6,2],[6,5,6,6],[7,1,7,2],[7,5,7,6],[8,1,8,2],[8,5,8,6],[9,1,9,2],[9,5,9,6],[10,1,10,2],[10,5,10,6],[11,0,11,6]]}
[null,"海淀区翠微中里16号楼改造工程",{"$nulls":4},"工程"]
[]
["招标工程量清单"]
[]
["招  标  人:",{"$nulls":3},"造价咨询人:"]
[null,"\n(单位盖章)",{"$nulls":3},"\n(单位资质专用章)"]
["法定代表人\n或其授权人:",{"$nulls":3},"法定代表人\n或其授权人:"]
[null,"\n(签字或盖章)",{"$nulls":3},"\n(签字或盖章)"]
["编  制  人:",{"$nulls":3},"复  核  人:"]
[null,"\n(造价人员签字盖专用章)",{"$nulls":3},"\n(造价工程师签字盖专用章)"]
["编制时间:",{"$nulls":3},"复核时间:"]
["安徽省建设工程造价计价软件测评合格编号2018JS-06"]

{"sheet":"C 招标说明","index":2,"n_rows":5,"n_cols":2,"rows_kept":5,"merged":[[0,0,0,1],[2,0,3,1],[4,0,4,1]]}
["总说明"]
["工程名称:海淀区翠微中里16号楼改造工程","第1页 共1页"]
["一、工程概况\n1、工程名称：海淀区翠微中里16号楼改造工程\n2、工程地点：本工程位于北京市海淀区\n二、编制依据\n1、《建设工程工程量清单计价规范》（2018版）；\n2、《安徽省建设工程工程量清单计价规范》（2018版）；\n3、现行的建筑工程施工规范与工程质量验收标准；\n4、《关于深化增值税改革有关政策的公告》\n三、编制说明\n1、工程量计算均执行《安徽省建设工程工程量清单计价规范》(2018版)的规定；\n2、投标报价时均应包括《安徽省建设工程工程量清单计价规范》(2018版)规定的全部工作内容，报价时还应包括施工损耗及规范规定的富余数量的费用；\n3、该工程量清单中每个子目的“项目特征” 未说明或说明不全的，均按照施工图及现场踏勘和施工规范要求执行，清单描述仅做依据之一；\n4、未说明的其余事项均按《建设工程工程量清单计价规范》要求执行；\n5、清单中措施费用投标单位根据现场踏勘及自己的施工组织设计自行测算、中标后该费用不再调整；\n6、工程检测、材料试验费含常规、非常规实验等费用，投标单位总价包干，业主不承担任何费用；\n7、各报价（综合单价）应考虑同时满足项目特征、图纸、图集、现场踏勘、强制规范、技术标准等内容；\n8、措施项目清单中未注明的措施项目均包含在其他施工技术措施费和其他施工组织措施费中，由各投标单位根据实际情况自行报价，决算时不再调整；\n9、原场地内建筑垃圾外运，由投标人考察现场，综合考虑在报价中；\n10、投标单位应按照安徽省建设工程造价管理总站下发的《关于调整我省现行建设工程计价依据增值税税率的通知》（造价[2019]7号文）、《关于调整我省现行建设工程计价依据增值税税率的通知》及《关于深化增值税改革有关政策的公告》的文件精神自行调整,考虑在报价文件中。\n11、本工程量结合图纸及现场情况计算，结算以实际丈量为准，本清单工程量不作为结算依据。\n12、投标人对工程量清单有任何疑问，应于招标文件规定的疑问提交截止日前提出，否则视为投标人认可该工程量清单已包括了招标范围内的全部内容。\n"]
[]
["安徽省建设工程造价计价软件测评合格编号2018JS-06"]

{"sheet":"1.2 E.1 分部分项工程量清单计价表","index":3,"n_rows":236,"n_cols":14,"rows_kept":236,"merged":[[0,0,0,13],[1,0,1,5],[1,6,1,10],[1,11,1,13],[2,0,4,0],[2,1,4,1],[2,2,4,3],[2,4,4,4],[2,5,4,6],[2,7,4,7],[2,8,2,13],[3,8,4,8],[3,9,4,9],[3,10,3,13],[4,10,4,11],[5,2,5,3],[5,5,5,6],[5,10,5,11],[6,2,6,3],[6,5,6,6],[6,10,6,11],[7,2,7,3],[7,5,7,6],[7,10,7,11],[8,2,8,3],[8,5,8,6],[8,10,8,11],[9,2,9,3],[9,5,9,6],[9,10,9,11],[10,2,10,3],[10,5,10,6],[10,10,10,11],[11,2,11,3],[11,5,11,6],[11,10,11,11],[12,2,12,3],[12,5,12,6],[12,10,12,11],[13,2,13,3],[13,5,13,6],[13,10,13,11],[14,2,14,3],[14,5,14,6],[14,10,14,11],[15,2,15,3],[15,5,15,6],[15,10,15,11],[16,2,16,3],[16,5,16,6],[16,10,16,11],[17,2,17,3],[17,5,17,6],[17,10,17,11],[18,2,18,3],[18,5,18,6],[18,10,18,11],[19,2,19,3],[19,5,19,6],[19,10,19,11],[20,2,20,3],[20,5,20,6],[20,10,20,11],[21,2,21,3],[21,5,21,6],[21,10,21,11],[22,2,22,3],[22,5,22,6],[22,10,22,11],[23,2,23,3],[23,5,23,6],[23,10,23,11],[24,2,24,3],[24,5,24,6],[24,10,24,11],[25,2,25,3],[25,5,25,6],[25,10,25,11],[26,0,26,13],[27,3,27,13],[28,0,28,13],[29,0,29,5],[29,6,29,10],[29,11,29,13],[30,0,32,0],[30,1,32,1],[30,2,32,3],[30,4,32,4],[30,5,32,6],[30,7,32,7],[30,8,30,13],[31,8,32,8],[31,9,32,9],[31,10,31,13],[32,10,32,11],[33,2,33,3],[33,5,33,6],[33,10,33,11],[34,2,34,3],[34,5,34,6],[34,10,34,11],[35,2,35,3],[35,5,35,6],[35,10,35,11],[36,2,36,3],[36,5,36,6],[36,10,36,11],[37,2,37,3],[37,5,37,6],[37,10,37,11],[38,2,38,3],[38,5,38,6],[38,10,38,11],[39,2,39,3],[39,5,39,6],[39,10,39,11],[40,2,40,3],[40,5,40,6],[40,10,40,11],[41,2,41,3],[41,5,41,6],[41,10,41,11],[42,2,42,3],[42,5,42,6],[42,10,42,11],[43,2,43,3],[43,5,43,6],[43,10,43,11],[44,2,44,3],[44,5,44,6],[44,10,44,11],[45,2,45,3],[45,5,45,6],[45,10,45,11],[46,2,46,3],[46,5,46,6],[46,10,46,11],[47,2,47,3],[47,5,47,6],[47,10,47,11],[48,2,48,3],[48,5,48,6],[48,10,48,11],[49,2,49,3],[49,5,49,6],[49,10,49,11],[50,2,50,3],[50,5,50,6],[50,10,50,11],[51,2,51,3],[51,5,51,6],[51,10,51,11],[52,2,52,3],[52,5,52,6],[52,10,52,11],[53,2,53,3],[53,5,53,6],[53,10,53,11],[54,2,54,3],[54,5,54,6],[54,10,54,11],[55,0,55,13],[56,3,56,13],[57,0,57,13],[58,0,58,5],[58,6,58,10],[58,11,58,13],[59,0,61,0],[59,1,61,1],[59,2,61,3],[59,4,61,4],[59,5,61,6],[59,7,61,7],[59,8,59,13],[60,8,61,8],[60,9,61,9],[60,10,60,13],[61,10,61,11],[62,2,62,3],[62,5,62,6],[62,10,62,11],[63,2,63,3],[63,5,63,6],[63,10,63,11],[64,2,64,3],[64,5,64,6],[64,10,64,11],[65,2,65,3],[65,5,65,6],[65,10,65,11],[66,2,66,3],[66,5,66,6],[66,10,66,11],[67,2,67,3],[67,5,67,6],[67,10,67,11],[68,2,68,3],[68,5,68,6],[68,10,68,11],[69,2,69,3],[69,5,69,6],[69,10,69,11],[70,2,70,3],[70,5,70,6],[70,10,70,11],[71,2,71,3],[71,5,71,6],[71,10,71,11],[72,2,72,3],[72,5,72,6],[72,10,72,11],[73,2,73,3],[73,5,73,6],[73,10,73,11],[74,2,74,3],[74,5,74,6],[74,10,74,11],[75,2,75,3],[75,5,75,6],[75,10,75,11],[76,2,76,3],[76,5,76,6],[76,10,76,11],[77,2,77,3],[77,5,77,6],[77,10,77,11],[78,2,78,3],[78,5,78,6],[78,10,78,11],[79,2,79,3],[79,5,79,6],[79,10,79,11],[80,2,80,3],[80,5,80,6],[80,10,80,11],[81,2,81,3],[81,5,81,6],[81,10,81,11],[82,2,82,3],[82,5,82,6],[82,10,82,11],[83,2,83,3],[83,5,83,6],[83,10,83,11],[84,2,84,3],[84,5,84,6],[84,10,84,11],[85,0,85,13],[86,3,86,13],[87,0,87,13],[88,0,88,5],[88,6,88,10],[88,11,88,13],[89,0,91,0],[89,1,91,1],[89,2,91,3],[89,4,91,4],[89,5,91,6],[89,7,91,7],[89,8,89,13],[90,8,91,8],[90,9,91,9],[90,10,90,13],[91,10,91,11],[92,2,92,3],[92,5,92,6],[92,10,92,11],[93,2,93,3],[93,5,93,6],[93,10,93,11],[94,2,94,3],[94,5,94,6],[94,10,94,11],[95,2,95,3],[95,5,95,6],[95,10,95,11],[96,2,96,3],[96,5,96,6],[96,10,96,11],[97,2,97,3],[97,5,97,6],[97,10,97,11],[98,2,98,3],[98,5,98,6],[98,10,98,11],[99,2,99,3],[99,5,99,6],[99,10,99,11],[100,2,100,3],[100,5,100,6],[100,10,100,11],[101,2,101,3],[101,5,101,6],[101,10,101,11],[102,2,102,3],[102,5,102,6],[102,10,102,11],[103,2,103,3],[103,5,103,6],[103,10,103,11],[104,2,104,3],[104,5,104,6],[104,10,104,11],[105,2,105,3],[105,5,105,6],[105,10,105,11],[106,2,106,3],[106,5,106,6],[106,10,106,11],[107,2,107,3],[107,5,107,6],[107,10,107,11],[108,2,108,3],[108,5,108,6],[108,10,108,11],[109,2,109,3],[109,5,109,6],[109,10,109,11],[110,2,110,3],[110,5,110,6],[110,10,110,11],[111,2,111,3],[111,5,111,6],[111,10,111,11],[112,2,112,3],[112,5,112,6],[112,10,112,11],[113,2,113,3],[113,5,113,6],[113,10,113,11],[114,2,114,3],[114,5,114,6],[114,10,114,11],[115,2,115,3],[115,5,115,6],[115,10,115,11],[116,0,116,13],[118,3,118,13],[119,0,119,13],[120,0,120,5],[120,6,120,10],[120,11,120,13],[121,0,123,0],[121,1,123,1],[121,2,123,3],[121,4,123,4],[121,5,123,6],[121,7,123,7],[121,8,121,13],[122,8,123,8],[122,9,123,9],[122,10,122,13],[123,10,123,11],[124,2,124,3],[124,5,124,6],[124,10,124,11],[125,2,125,3],[125,5,125,6],[125,10,125,11],[126,2,126,3],[126,5,126,6],[126,10,126,11],[127,2,127,3],[127,5,127,6],[127,10,127,11],[128,2,128,3],[128,5,128,6],[128,10,128,11],[129,2,129,3],[129,5,129,6],[129,10,129,11],[130,2,130,3],[130,5,130,6],[130,10,130,11],[131,2,131,3],[131,5,131,6],[131,10,131,11],[132,2,132,3],[132,5,132,6],[132,10,132,11],[133,2,133,3],[133,5,133,6],[133,10,133,11],[134,2,134,3],[134,5,134,6],[134,10,134,11],[135,2,135,3],[135,5,135,6],[135,10,135,11],[136,2,136,3],[136,5,136,6],[136,10,136,11],[137,2,137,3],[137,5,137,6],[137,10,137,11],[138,2,138,3],[138,5,138,6],[138,10,138,11],[139,2,139,3],[139,5,139,6],[139,10,139,11],[140,2,140,3],[140,5,140,6],[140,10,140,11],[141,2,141,3],[141,5,141,6],[141,10,141,11],[142,2,142,3],[142,5,142,6],[142,10,142,11],[143,2,143,3],[143,5,143,6],[143,10,143,11],[144,0,144,13],[145,3,145,13],[146,0,146,13],[147,0,147,5],[147,6,147,10],[147,11,147,13],[148,0,150,0],[148,1,150,1],[148,2,150,3],[148,4,150,4],[148,5,150,6],[148,7,150,7],[148,8,148,13],[149,8,150,8],[149,9,150,9],[149,10,149,13],[150,10,150,11],[151,2,151,3],[151,5,151,6],[151,10,151,11],[152,2,152,3],[152,5,152,6],[152,10,152,11],[153,2,153,3],[153,5,153,6],[153,10,153,11],[154,2,154,3],[154,5,154,6],[154,10,154,11],[155,2,155,3],[155,5,155,6],[155,10,155,11],[156,2,156,3],[156,5,156,6],[156,10,156,11],[157,2,157,3],[157,5,157,6],[157,10,157,11],[158,2,158,3],[158,5,158,6],[158,10,158,11],[159,2,159,3],[159,5,159,6],[159,10,159,11],[160,2,160,3],[160,5,160,6],[160,10,160,11],[161,2,161,3],[161,5,161,6],[161,10,161,11],[162,2,162,3],[162,5,162,6],[162,10,162,11],[163,2,163,3],[163,5,163,6],[163,10,163,11],[164,2,164,3],[164,5,164,6],[164,10,164,11],[165,2,165,3],[165,5,165,6],[165,10,165,11],[166,2,166,3],[166,5,166,6],[166,10,166,11],[167,2,167,3],[167,5,167,6],[167,10,167,11],[168,2,168,3],[168,5,168,6],[168,10,168,11],[169,2,169,3],[169,5,169,6],[169,10,169,11],[170,2,170,3],[170,5,170,6],[170,10,170,11],[171,2,171,3],[171,5,171,6],[171,10,171,11],[172,2,172,3],[172,5,172,6],[172,10,172,11],[173,2,173,3],[173,5,173,6],[173,10,173,11],[174,0,174,13],[176,3,176,13],[177,0,177,13],[178,0,178,5],[178,6,178,10],[178,11,178,13],[179,0,181,0],[179,1,181,1],[179,2,181,3],[179,4,181,4],[179,5,181,6],[179,7,181,7],[179,8,179,13],[180,8,181,8],[180,9,181,9],[180,10,180,13],[181,10,181,11],[182,2,182,3],[182,5,182,6],[182,10,182,11],[183,2,183,3],[183,5,183,6],[183,10,183,11],[184,2,184,3],[184,5,184,6],[184,10,184,11],[185,2,185,3],[185,5,185,6],[185,10,185,11],[186,2,186,3],[186,5,186,6],[186,10,186,11],[187,2,187,3],[187,5,187,6],[187,10,187,11],[188,2,188,3],[188,5,188,6],[188,10,188,11],[189,2,189,3],[189,5,189,6],[189,10,189,11],[190,2,190,3],[190,5,190,6],[190,10,190,11],[191,2,191,3],[191,5,191,6],[191,10,191,11],[192,2,192,3],[192,5,192,6],[192,10,192,11],[193,2,193,3],[193,5,193,6],[193,10,193,11],[194,2,194,3],[194,5,194,6],[194,10,194,11],[195,2,195,3],[195,5,195,6],[195,10,195,11],[196,2,196,3],[196,5,196,6],[196,10,196,11],[197,2,197,3],[197,5,197,6],[197,10,197,11],[198,2,198,3],[198,5,198,6],[198,10,198,11],[199,2,199,3],[199,5,199,6],[199,10,199,11],[200,2,200,3],[200,5,200,6],[200,10,200,11],[201,2,201,3],[201,5,201,6],[201,10,201,11],[202,0,202,13],[203,3,203,13],[204,0,204,13],[205,0,205,5],[205,6,205,10],[205,11,205,13],[206,0,208,0],[206,1,208,1],[206,2,208,3],[206,4,208,4],[206,5,208,6],[206,7,208,7],[206,8,206,13],[207,8,208,8],[207,9,208,9],[207,10,207,13],[208,10,208,11],[209,2,209,3],[209,5,209,6],[209,10,209,11],[210,2,210,3],[210,5,210,6],[210,10,210,11],[211,2,211,3],[211,5,211,6],[211,10,211,11],[212,2,212,3],[212,5,212,6],[212,10,212,11],[213,2,213,3],[213,5,213,6],[213,10,213,11],[214,2,214,3],[214,5,214,6],[214,10,214,11],[215,2,215,3],[215,5,215,6],[215,10,215,11],[216,2,216,3],[216,5,216,6],[216,10,216,11],[217,2,217,3],[217,5,217,6],[217,10,217,11],[218,2,218,3],[218,5,218,6],[218,10,218,11],[219,2,219,3],[219,5,219,6],[219,10,219,11],[220,2,220,3],[220,5,220,6],[220,10,220,11],[221,2,221,3],[221,5,221,6],[221,10,221,11],[222,2,222,3],[222,5,222,6],[222,10,222,11],[223,2,223,3],[223,5,223,6],[223,10,223,11],[224,2,224,3],[224,5,224,6],[224,10,224,11],[225,2,225,3],[225,5,225,6],[225,10,225,11],[226,2,226,3],[226,5,226,6],[226,10,226,11],[227,2,227,3],[227,5,227,6],[227,10,227,11],[228,2,228,3],[228,5,228,6],[228,10,228,11],[229,2,229,3],[229,5,229,6],[229,10,229,11],[230,2,230,3],[230,5,230,6],[230,10,230,11],[231,2,231,3],[231,5,231,6],[231,10,231,11],[232,2,232,3],[232,5,232,6],[232,10,232,11],[233,2,233,3],[233,5,233,6],[233,10,233,11],[234,0,234,13],[235,3,235,13]]}
["E.1 分部分项工程量清单计价表"]
["工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第1页 共8页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
[null,null,"单项工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":4},""]
[null,null,"单位工程名称：5、6、11、12、13号",{"$nulls":4},""]
["1","011606003001","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["2","ZB010101001001","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["3","011610001001","门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["4","011614003001","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["5","011406003001","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["6","011406001001","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["7","011406003002","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["8","011406001002","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["9","011406001003","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"8.780"]
["10","011606001001","卫生间区域地面拆除及粉刷",null,"1、人工及下运","m2",null,"2.770"]
["11","010904001001","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["12","041001006001","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["13","010201001001","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["14","ZB010101001002","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["15","010402001001","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"29.900"]
["16","010402001002","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"42.500"]
["17","011606003002","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["18","ZB010101001003","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["19","041001006002","包管拆除",null,"1、人工及下运","个",null,"4.000"]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第2页 共8页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["20","011610001002","门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["21","011614003002","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["22","011406003003","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["23","011406001004","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["24","011406003004","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["25","011406001005","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["26","011406001006","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"8.780"]
["27","011606001002","卫生间区域地面拆除及粉刷",null,"1、人工及下运","m2",null,"2.770"]
["28","010201001002","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["29","010904001002","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["30","ZB010101001004","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["31","010402001003","新建墙体及双面粉刷",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"29.900"]
["32","010402001004","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"42.500"]
["33","011601001003","背景墙拆除",null,"1、现有墙体拆除","m2",null,"16.000"]
["34","011606003003","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["35","ZB010101001005","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["36","011406001007","背景墙拆除后墙面腻子及乳胶漆处理",null,null,"m2",null,"16.000"]
["37","041001006003","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["38","011610001003","阳台门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["39","011614003003","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["40","011406003005","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["41","011406001008","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第3页 共8页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["42","011406003006","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["43","011406001009","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["44","011406001010","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"8.780"]
["45","011606001003","卫生间区域地面拆除及粉刷",null,"1、人工及下运","m2",null,"2.770"]
["46","010201001003","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["47","010904001003","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["48","ZB010101001006","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["49","010402001005","新建墙体及双面粉刷",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"29.900"]
["50","010402001006","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"40.500"]
["51","011601001004","背景墙拆除",null,"1、现有墙体拆除","m2",null,"13.500"]
["52","011606003004","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["53","ZB010101001007","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["54","011406001011","背景墙拆除后墙面腻子及乳胶漆处理",null,"1、人工及主材","m2",null,"13.500"]
["55","041001006004","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["56","011610001004","阳台门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["57","011614002001","柜体拆除",null,"1、人工及外运","项",null,"1.000"]
["58","011614003004","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["59","011406003007","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["60","011406001012","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["61","011406003008","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["62","011406001013","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["63","011406001014","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"8.780"]
[]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第4页 共8页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["64","011606001004","卫生间区域地面拆除及粉刷",null,"1、人工及下运","m2",null,"2.770"]
["65","010201001004","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["66","010904001004","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["67","ZB010101001008","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["68","010402001007","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"29.900"]
["69","010402001008","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"40.500"]
["70","011601001005","墙体拆除",null,"1、现有墙体拆除","m2",null,"22.560"]
["71","011606003005","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["72","ZB010101001009","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["73","011610001005","门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["74","041001006005","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["75","011614003005","门套拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["76","011601001006","背景墙拆除",null,"1、现有墙体拆除","m2",null,"11.500"]
["77","011615001001","开门洞",null,null,"个",null,"1.000"]
["78","010801001001","安装入户门",null,"1、人工及下运","个",null,"1.000"]
["79","011601001007","砖砌体拆除",null,null,"项",null,"1.000"]
["80","011406003009","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["81","011406001015","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["82","011614003006","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["83","011406003010","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["84","011406001016","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["85","011406003011","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["86","011406001017","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
[]
[]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第5页 共8页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["87","010904001005","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"14.500"]
["88","011612002001","马桶拆除",null,"1、人工及下运","个",null,"1.000"]
["89","011614002002","浴室柜拆除",null,"1、人工及下运","项",null,"1.000"]
["90","011614002003","橱柜拆除",null,"1、人工及下运","m",null,"3.700"]
["91","011606001005","现有卫生间地台拆除（高度20公分)",null,"1、人工及下运","m2",null,"3.500"]
["92","011101001001","现有卫生间地台拆除后粉刷",null,"1、人工及辅材","m2",null,"3.500"]
["93","010201001005","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["94","010904001006","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["95","ZB010101001010","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["96","010402001009","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"31.200"]
["97","010402001010","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"43.200"]
["98","WB011614004001","建筑垃圾外运",null,"1、1项约50平方约4000元清运费","项",null,"5.000"]
["99","ZB010101001011","卫生间水电改造",null,"1、人工及辅材（1.马桶下水及进水2.浴室柜进水及下水 3.淋浴进水及下水）","项",null,"5.000"]
[null,null,"单位工程名称：7~10号",{"$nulls":4},""]
["1","011615001001","开门洞",null,"1、现有墙体拆除","个",null,"2.000"]
["2","011610001002","门拆除",null,"1、成套门","个",null,"2.000"]
["3","010402001003","封门洞",null,"1、加气块及双面粉刷","个",null,"2.000"]
["4","ZB010101001003","封门洞双面局部腻子及乳胶漆处理",null,null,"项",null,"2.000"]
["5","011101001001","地台拆除地砖及粉刷",null,"1、人工及辅材","m2",null,"3.600"]
["6","011406001005","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"9.540"]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第6页 共8页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["7","010904001002","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"14.500"]
["8","011614003001","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["9","011406003001","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["10","011406001001","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["11","011406003002","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["12","041001006002","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["13","011606003001","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"30.300"]
["14","ZB010101001001","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["15","ZB010101001002","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"8.500"]
["16","010402001001","新建墙体及双面粉刷（卫生间到顶）",null,"1、加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"18.800"]
["17","010402001002","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷","m2",null,"25.000"]
["18","011601001001","墙体拆除",null,"1、现有墙体拆除","m2",null,"9.800"]
["19","011606003002","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["20","ZB010101001004","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["21","041001006003","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["22","011614002004","柜子拆除",null,"1、人工及下运","个",null,"1.000"]
["23","011614002005","浴室柜子拆除（1.94米长）",null,"1、人工及下运","个",null,"1.000"]
["24","011606001002","楼地面龙骨及饰面拆除",null,"1、地台拆除，含人工及下运","m2",null,"5.200"]
["25","011101001003","水泥砂浆楼地面",null,"1、地台拆除后粉刷（高度20公分)","m2",null,"9.000"]
["26","011606003003","天棚面龙骨及饰面拆除",null,"1、集成吊顶拆除，含人工及下运","m2",null,"5.200"]
["27","011614003004","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["28","011406003007","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["29","011406001012","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
[]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第7页 共8页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["30","011406003008","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["31","011406001013","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["32","011601001003","背景墙拆除",null,"1、现有墙体拆除","m2",null,"8.500"]
["33","011406001011","背景墙拆除后墙面腻子及乳胶漆处理",null,"1、人工及主材","m2",null,"8.500"]
["34","ZB010101001006","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"8.500"]
["35","010402001006","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"18.800"]
["36","010402001007","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"25.000"]
["37","ZB010101001007","油烟机拆除",null,"1、人工及下运","项",null,"1.000"]
["38","011615001002","开门洞",null,null,"个",null,"1.000"]
["39","011606003004","天棚面龙骨及饰面拆除",null,"1、集成吊顶拆除，含人工及下运","m2",null,"22.500"]
["40","ZB010101001008","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["41","011614003005","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["42","011406003009","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["43","011406001014","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["44","041001006001","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["45","010201001001","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["46","010904001001","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["47","ZB010101001009","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"3.500"]
["48","010402001008","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"7.200"]
["49","010402001009","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"14.400"]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：海淀区翠微中里16号楼改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第8页 共8页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["50","WB011614004001","建筑垃圾外运",null,"1、1项约50平方约4000元清运费","项",null,"3.000"]
["51","ZB010101001011","卫生间水电改造",null,"1、人工及辅材（1.马桶下水及进水2.浴室柜进水及下水 3.淋浴进水及下水）","间",null,"2.000"]
[null,null,"单位工程名称：922室修补项目",{"$nulls":4},""]
["1","011615001001","1022阳台地面铲除",null,"人工及下运","项",null,"1.000"]
["2","011615001002","1022阳台地面水泥沙粉平",null,"人工及下运","项",null,"1.000"]
["3","011615001003","1022阳台墙面打磨至50公分高",null,"人工及下运","项",null,"1.000"]
["4","011615001004","1022阳台墙面地面防水",null,"东方雨虹，地面全刷，墙面0.5米高","项",null,"1.000"]
["5","011615001005","1022阳台墙面地面防水后粉刷",null,"东方雨虹，地面全刷，墙面0.5米高","项",null,"1.000"]
["6","011615001006","922室阳台顶面及墙面铲除",null,"人工","项",null,"1.000"]
["7","011615001007","922室阳台顶面腻子修补及乳胶漆",null,"基层处理 腻子两遍打磨后两遍面漆","项",null,"1.000"]
["8","011615001008","卫生间顶面拆除",null,"人工及下运","项",null,"1.000"]
["9","011615001009","卫生间顶面集成吊顶及灯更换300*300",null,"铝扣板，边条，龙骨，吊筋，人工，300*300方灯及换气扇","项",null,"1.000"]
{"$rows_empty":14}
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"3.1 E.1 分部分项工程量清单计价表(所有标题)","index":4,"n_rows":151,"n_cols":14,"rows_kept":151,"merged":[[0,0,0,13],[1,0,1,5],[1,6,1,10],[1,11,1,13],[2,0,4,0],[2,1,4,1],[2,2,4,3],[2,4,4,4],[2,5,4,6],[2,7,4,7],[2,8,2,13],[3,8,4,8],[3,9,4,9],[3,10,3,13],[4,10,4,11],[5,2,5,4],[5,5,5,6],[5,10,5,11],[6,2,6,3],[6,5,6,6],[6,10,6,11],[7,2,7,3],[7,5,7,6],[7,10,7,11],[8,2,8,3],[8,5,8,6],[8,10,8,11],[9,2,9,3],[9,5,9,6],[9,10,9,11],[10,2,10,3],[10,5,10,6],[10,10,10,11],[11,2,11,3],[11,5,11,6],[11,10,11,11],[12,2,12,3],[12,5,12,6],[12,10,12,11],[13,2,13,3],[13,5,13,6],[13,10,13,11],[14,2,14,3],[14,5,14,6],[14,10,14,11],[15,2,15,3],[15,5,15,6],[15,10,15,11],[16,2,16,3],[16,5,16,6],[16,10,16,11],[17,2,17,3],[17,5,17,6],[17,10,17,11],[18,2,18,3],[18,5,18,6],[18,10,18,11],[19,2,19,3],[19,5,19,6],[19,10,19,11],[20,2,20,3],[20,5,20,6],[20,10,20,11],[21,2,21,3],[21,5,21,6],[21,10,21,11],[22,2,22,4],[22,5,22,6],[22,10,22,11],[23,2,23,4],[23,5,23,6],[23,10,23,11],[24,2,24,3],[24,5,24,6],[24,10,24,11],[25,2,25,3],[25,5,25,6],[25,10,25,11],[26,2,26,3],[26,5,26,6],[26,10,26,11],[27,2,27,3],[27,5,27,6],[27,10,27,11],[28,2,28,3],[28,5,28,6],[28,10,28,11],[29,0,29,13],[30,3,30,13],[31,0,31,13],[32,0,32,5],[32,6,32,10],[32,11,32,13],[33,0,35,0],[33,1,35,1],[33,2,35,3],[33,4,35,4],[33,5,35,6],[33,7,35,7],[33,8,33,13],[34,8,35,8],[34,9,35,9],[34,10,34,13],[35,10,35,11],[36,2,36,3],[36,5,36,6],[36,10,36,11],[37,2,37,3],[37,5,37,6],[37,10,37,11],[38,2,38,3],[38,5,38,6],[38,10,38,11],[39,2,39,3],[39,5,39,6],[39,10,39,11],[40,2,40,3],[40,5,40,6],[40,10,40,11],[41,2,41,3],[41,5,41,6],[41,10,41,11],[42,2,42,3],[42,5,42,6],[42,10,42,11],[43,2,43,3],[43,5,43,6],[43,10,43,11],[44,2,44,3],[44,5,44,6],[44,10,44,11],[45,2,45,3],[45,5,45,6],[45,10,45,11],[46,2,46,3],[46,5,46,6],[46,10,46,11],[47,2,47,3],[47,5,47,6],[47,10,47,11],[48,2,48,4],[48,5,48,6],[48,10,48,11],[49,2,49,4],[49,5,49,6],[49,10,49,11],[50,2,50,3],[50,5,50,6],[50,10,50,11],[51,2,51,3],[51,5,51,6],[51,10,51,11],[52,2,52,3],[52,5,52,6],[52,10,52,11],[53,2,53,3],[53,5,53,6],[53,10,53,11],[54,2,54,3],[54,5,54,6],[54,10,54,11],[55,2,55,3],[55,5,55,6],[55,10,55,11],[56,2,56,3],[56,5,56,6],[56,10,56,11],[57,2,57,3],[57,5,57,6],[57,10,57,11],[58,2,58,3],[58,5,58,6],[58,10,58,11],[59,0,59,13],[60,3,60,13],[61,0,61,13],[62,0,62,5],[62,6,62,10],[62,11,62,13],[63,0,65,0],[63,1,65,1],[63,2,65,3],[63,4,65,4],[63,5,65,6],[63,7,65,7],[63,8,63,13],[64,8,65,8],[64,9,65,9],[64,10,64,13],[65,10,65,11],[66,2,66,3],[66,5,66,6],[66,10,66,11],[67,2,67,3],[67,5,67,6],[67,10,67,11],[68,2,68,3],[68,5,68,6],[68,10,68,11],[69,2,69,3],[69,5,69,6],[69,10,69,11],[70,2,70,3],[70,5,70,6],[70,10,70,11],[71,2,71,3],[71,5,71,6],[71,10,71,11],[72,2,72,3],[72,5,72,6],[72,10,72,11],[73,2,73,3],[73,5,73,6],[73,10,73,11],[74,2,74,3],[74,5,74,6],[74,10,74,11],[75,2,75,4],[75,5,75,6],[75,10,75,11],[76,2,76,4],[76,5,76,6],[76,10,76,11],[77,2,77,3],[77,5,77,6],[77,10,77,11],[78,2,78,3],[78,5,78,6],[78,10,78,11],[79,2,79,3],[79,5,79,6],[79,10,79,11],[80,2,80,3],[80,5,80,6],[80,10,80,11],[81,2,81,3],[81,5,81,6],[81,10,81,11],[82,2,82,3],[82,5,82,6],[82,10,82,11],[83,2,83,3],[83,5,83,6],[83,10,83,11],[84,2,84,3],[84,5,84,6],[84,10,84,11],[85,2,85,3],[85,5,85,6],[85,10,85,11],[86,2,86,3],[86,5,86,6],[86,10,86,11],[87,2,87,3],[87,5,87,6],[87,10,87,11],[88,2,88,3],[88,5,88,6],[88,10,88,11],[89,0,89,13],[90,3,90,13],[91,0,91,13],[92,0,92,5],[92,6,92,10],[92,11,92,13],[93,0,95,0],[93,1,95,1],[93,2,95,3],[93,4,95,4],[93,5,95,6],[93,7,95,7],[93,8,93,13],[94,8,95,8],[94,9,95,9],[94,10,94,13],[95,10,95,11],[96,2,96,3],[96,5,96,6],[96,10,96,11],[97,2,97,3],[97,5,97,6],[97,10,97,11],[98,2,98,3],[98,5,98,6],[98,10,98,11],[99,2,99,3],[99,5,99,6],[99,10,99,11],[100,2,100,3],[100,5,100,6],[100,10,100,11],[101,2,101,3],[101,5,101,6],[101,10,101,11],[102,2,102,3],[102,5,102,6],[102,10,102,11],[103,2,103,4],[103,5,103,6],[103,10,103,11],[104,2,104,4],[104,5,104,6],[104,10,104,11],[105,2,105,3],[105,5,105,6],[105,10,105,11],[106,2,106,3],[106,5,106,6],[106,10,106,11],[107,2,107,3],[107,5,107,6],[107,10,107,11],[108,2,108,3],[108,5,108,6],[108,10,108,11],[109,2,109,3],[109,5,109,6],[109,10,109,11],[110,2,110,3],[110,5,110,6],[110,10,110,11],[111,2,111,3],[111,5,111,6],[111,10,111,11],[112,2,112,3],[112,5,112,6],[112,10,112,11],[113,2,113,3],[113,5,113,6],[113,10,113,11],[114,2,114,3],[114,5,114,6],[114,10,114,11],[115,2,115,3],[115,5,115,6],[115,10,115,11],[116,2,116,3],[116,5,116,6],[116,10,116,11],[117,2,117,3],[117,5,117,6],[117,10,117,11],[118,2,118,3],[118,5,118,6],[118,10,118,11],[119,2,119,3],[119,5,119,6],[119,10,119,11],[120,0,120,13],[121,3,121,13],[122,0,122,13],[123,0,123,5],[123,6,123,10],[123,11,123,13],[124,0,126,0],[124,1,126,1],[124,2,126,3],[124,4,126,4],[124,5,126,6],[124,7,126,7],[124,8,124,13],[125,8,126,8],[125,9,126,9],[125,10,125,13],[126,10,126,11],[127,2,127,3],[127,5,127,6],[127,10,127,11],[128,2,128,3],[128,5,128,6],[128,10,128,11],[129,2,129,3],[129,5,129,6],[129,10,129,11],[130,2,130,3],[130,5,130,6],[130,10,130,11],[131,2,131,3],[131,5,131,6],[131,10,131,11],[132,2,132,3],[132,5,132,6],[132,10,132,11],[133,2,133,3],[133,5,133,6],[133,10,133,11],[134,2,134,3],[134,5,134,6],[134,10,134,11],[135,2,135,3],[135,5,135,6],[135,10,135,11],[136,2,136,3],[136,5,136,6],[136,10,136,11],[137,2,137,3],[137,5,137,6],[137,10,137,11],[138,2,138,3],[138,5,138,6],[138,10,138,11],[139,2,139,3],[139,5,139,6],[139,10,139,11],[140,2,140,4],[140,5,140,6],[140,10,140,11],[141,2,141,4],[141,5,141,6],[141,10,141,11],[142,2,142,3],[142,5,142,6],[142,10,142,11],[143,2,143,3],[143,5,143,6],[143,10,143,11],[144,2,144,4],[144,5,144,6],[144,10,144,11],[145,2,145,3],[145,5,145,6],[145,10,145,11],[146,2,146,3],[146,5,146,6],[146,10,146,11],[147,2,147,3],[147,5,147,6],[147,10,147,11],[148,2,148,3],[148,5,148,6],[148,10,148,11],[149,0,149,13],[150,3,150,13]]}
["E.1 分部分项工程量清单计价表"]
["工程名称：5、6、11、12、13号",{"$nulls":5},"标段：",{"$nulls":4},"第1页 共5页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
[null,"5号",{"$nulls":5},""]
["1","011606003001","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["2","ZB010101001001","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["3","011610001001","门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["4","011614003001","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["5","011406003001","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["6","011406001001","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["7","011406003002","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["8","011406001002","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["9","011406001003","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"8.780"]
["10","011606001001","卫生间区域地面拆除及粉刷",null,"1、人工及下运","m2",null,"2.770"]
["11","010904001001","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["12","041001006001","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["13","010201001001","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["14","ZB010101001002","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["15","010402001001","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"29.900"]
["16","010402001002","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"42.500"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"6号",{"$nulls":5},""]
["17","011606003002","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["18","ZB010101001003","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["19","041001006002","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["20","011610001002","门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
[]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：5、6、11、12、13号",{"$nulls":5},"标段：",{"$nulls":4},"第2页 共5页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["21","011614003002","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["22","011406003003","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["23","011406001004","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["24","011406003004","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["25","011406001005","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["26","011406001006","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"8.780"]
["27","011606001002","卫生间区域地面拆除及粉刷",null,"1、人工及下运","m2",null,"2.770"]
["28","010201001002","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["29","010904001002","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["30","ZB010101001004","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["31","010402001003","新建墙体及双面粉刷",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"29.900"]
["32","010402001004","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"42.500"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"11号",{"$nulls":5},""]
["33","011601001003","背景墙拆除",null,"1、现有墙体拆除","m2",null,"16.000"]
["34","011606003003","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["35","ZB010101001005","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["36","011406001007","背景墙拆除后墙面腻子及乳胶漆处理",null,null,"m2",null,"16.000"]
["37","041001006003","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["38","011610001003","阳台门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["39","011614003003","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["40","011406003005","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["41","011406001008","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：5、6、11、12、13号",{"$nulls":5},"标段：",{"$nulls":4},"第3页 共5页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["42","011406003006","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["43","011406001009","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["44","011406001010","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"8.780"]
["45","011606001003","卫生间区域地面拆除及粉刷",null,"1、人工及下运","m2",null,"2.770"]
["46","010201001003","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["47","010904001003","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["48","ZB010101001006","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["49","010402001005","新建墙体及双面粉刷",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"29.900"]
["50","010402001006","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"40.500"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"12号",{"$nulls":5},""]
["51","011601001004","背景墙拆除",null,"1、现有墙体拆除","m2",null,"13.500"]
["52","011606003004","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["53","ZB010101001007","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["54","011406001011","背景墙拆除后墙面腻子及乳胶漆处理",null,"1、人工及主材","m2",null,"13.500"]
["55","041001006004","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["56","011610001004","阳台门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["57","011614002001","柜体拆除",null,"1、人工及外运","项",null,"1.000"]
["58","011614003004","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["59","011406003007","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["60","011406001012","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["61","011406003008","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["62","011406001013","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：5、6、11、12、13号",{"$nulls":5},"标段：",{"$nulls":4},"第4页 共5页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["63","011406001014","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"8.780"]
["64","011606001004","卫生间区域地面拆除及粉刷",null,"1、人工及下运","m2",null,"2.770"]
["65","010201001004","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["66","010904001004","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["67","ZB010101001008","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["68","010402001007","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"29.900"]
["69","010402001008","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"40.500"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"13号",{"$nulls":5},""]
["70","011601001005","墙体拆除",null,"1、现有墙体拆除","m2",null,"22.560"]
["71","011606003005","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
["72","ZB010101001009","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["73","011610001005","门拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["74","041001006005","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["75","011614003005","门套拆除",null,"1、卫生间门卧室门阳台门","个",null,"1.000"]
["76","011601001006","背景墙拆除",null,"1、现有墙体拆除","m2",null,"11.500"]
["77","011615001001","开门洞",null,null,"个",null,"1.000"]
["78","010801001001","安装入户门",null,"1、人工及下运","个",null,"1.000"]
["79","011601001007","砖砌体拆除",null,null,"项",null,"1.000"]
["80","011406003009","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["81","011406001015","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["82","011614003006","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["83","011406003010","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["84","011406001016","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：5、6、11、12、13号",{"$nulls":5},"标段：",{"$nulls":4},"第5页 共5页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["85","011406003011","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["86","011406001017","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["87","010904001005","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"14.500"]
["88","011612002001","马桶拆除",null,"1、人工及下运","个",null,"1.000"]
["89","011614002002","浴室柜拆除",null,"1、人工及下运","项",null,"1.000"]
["90","011614002003","橱柜拆除",null,"1、人工及下运","m",null,"3.700"]
["91","011606001005","现有卫生间地台拆除（高度20公分)",null,"1、人工及下运","m2",null,"3.500"]
["92","011101001001","现有卫生间地台拆除后粉刷",null,"1、人工及辅材","m2",null,"3.500"]
["93","010201001005","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["94","010904001006","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["95","ZB010101001010","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"12.000"]
["96","010402001009","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"31.200"]
["97","010402001010","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"43.200"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"其他",{"$nulls":5},""]
["98","WB011614004001","建筑垃圾外运",null,"1、1项约50平方约4000元清运费","项",null,"5.000"]
["99","ZB010101001011","卫生间水电改造",null,"1、人工及辅材（1.马桶下水及进水2.浴室柜进水及下水 3.淋浴进水及下水）","项",null,"5.000"]
[null,null,"分部小计",{"$nulls":4},""]
[]
[]
[]
[]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"3.2 附录F 措施项目清单计价表","index":5,"n_rows":44,"n_cols":9,"rows_kept":44,"merged":[[0,0,0,8],[1,0,1,3],[1,4,1,6],[1,7,1,8],[2,1,2,2],[2,3,2,4],[2,6,2,7],[3,1,3,2],[3,3,3,4],[3,6,3,7],[4,1,4,2],[4,3,4,4],[4,6,4,7],[5,1,5,2],[5,3,5,4],[5,6,5,7],[6,1,6,2],[6,3,6,4],[6,6,6,7],[7,1,7,2],[7,3,7,4],[7,6,7,7],[8,1,8,2],[8,3,8,4],[8,6,8,7],[9,1,9,2],[9,3,9,4],[9,6,9,7],[10,1,10,2],[10,3,10,4],[10,6,10,7],[11,1,11,2],[11,3,11,4],[11,6,11,7],[12,1,12,2],[12,3,12,4],[12,6,12,7],[13,1,13,2],[13,3,13,4],[13,6,13,7],[14,1,14,2],[14,3,14,4],[14,6,14,7],[15,1,15,2],[15,3,15,4],[15,6,15,7],[16,1,16,2],[16,3,16,4],[16,6,16,7],[17,1,17,2],[17,3,17,4],[17,6,17,7],[18,1,18,2],[18,3,18,4],[18,6,18,7],[19,1,19,2],[19,3,19,4],[19,6,19,7],[20,1,20,2],[20,3,20,4],[20,6,20,7],[21,1,21,2],[21,3,21,4],[21,6,21,7],[22,1,22,2],[22,3,22,4],[22,6,22,7],[23,1,23,2],[23,3,23,4],[23,6,23,7],[24,1,24,2],[24,3,24,4],[24,6,24,7],[25,1,25,2],[25,3,25,4],[25,6,25,7],[26,1,26,2],[26,3,26,4],[26,6,26,7],[27,1,27,2],[27,3,27,4],[27,6,27,7],[28,1,28,2],[28,3,28,4],[28,6,28,7],[29,1,29,2],[29,3,29,4],[29,6,29,7],[30,1,30,2],[30,3,30,4],[30,6,30,7],[31,1,31,2],[31,3,31,4],[31,6,31,7],[32,1,32,2],[32,3,32,4],[32,6,32,7],[33,1,33,2],[33,3,33,4],[33,6,33,7],[34,1,34,2],[34,3,34,4],[34,6,34,7],[35,1,35,2],[35,3,35,4],[35,6,35,7],[36,1,36,2],[36,3,36,4],[36,6,36,7],[37,1,37,2],[37,3,37,4],[37,6,37,7],[38,1,38,2],[38,3,38,4],[38,6,38,7],[39,1,39,2],[39,3,39,4],[39,6,39,7],[40,1,40,2],[40,3,40,4],[40,6,40,7],[41,0,41,7],[43,2,43,8]]}
["附录F 措施项目清单与计价表"]
["工程名称：5、6、11、12、13号",{"$nulls":3},"标段：",null,null,"第1页 共1页"]
["序号","项目编码",null,"项目名称",null,"计算基础","费率（%）",null,"金额（元）"]
["1","ZC-01",null,"夜间施工增加费",null,null,"0.500"]
["2","ZC-02",null,"二次搬运费",null,null,"1.200"]
["3","ZC-03",null,"冬雨季施工增加费",null,null,"0.700"]
["4","ZC-04",null,"已完工程及设备保护费",null,null,"0.500"]
["5","ZC-05",null,"工程定位复测费",null,null,"0.800"]
["6","ZC-06",null,"非夜间施工照明费",null,null,"0.400"]
["7","ZC-07",null,"临时保护设施费",null,null,"0.100"]
["8","ZC-08",null,"赶工措施费",null,null,"2.100"]
{"$rows_empty":30}
["合   计",{"$nulls":7},""]
[]
[null,null,"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"3.3 附录G 不可竞争项目清单与计价表","index":6,"n_rows":44,"n_cols":9,"rows_kept":44,"merged":[[0,0,0,8],[1,0,1,3],[1,4,1,6],[1,7,1,8],[2,1,2,2],[2,3,2,4],[2,6,2,7],[3,1,3,2],[3,3,3,4],[3,6,3,7],[4,1,4,2],[4,3,4,4],[4,6,4,7],[5,1,5,2],[5,3,5,4],[5,6,5,7],[6,1,6,2],[6,3,6,4],[6,6,6,7],[7,1,7,2],[7,3,7,4],[7,6,7,7],[8,1,8,2],[8,3,8,4],[8,6,8,7],[9,1,9,2],[9,3,9,4],[9,6,9,7],[10,1,10,2],[10,3,10,4],[10,6,10,7],[11,1,11,2],[11,3,11,4],[11,6,11,7],[12,1,12,2],[12,3,12,4],[12,6,12,7],[13,1,13,2],[13,3,13,4],[13,6,13,7],[14,1,14,2],[14,3,14,4],[14,6,14,7],[15,1,15,2],[15,3,15,4],[15,6,15,7],[16,1,16,2],[16,3,16,4],[16,6,16,7],[17,1,17,2],[17,3,17,4],[17,6,17,7],[18,1,18,2],[18,3,18,4],[18,6,18,7],[19,1,19,2],[19,3,19,4],[19,6,19,7],[20,1,20,2],[20,3,20,4],[20,6,20,7],[21,1,21,2],[21,3,21,4],[21,6,21,7],[22,1,22,2],[22,3,22,4],[22,6,22,7],[23,1,23,2],[23,3,23,4],[23,6,23,7],[24,1,24,2],[24,3,24,4],[24,6,24,7],[25,1,25,2],[25,3,25,4],[25,6,25,7],[26,1,26,2],[26,3,26,4],[26,6,26,7],[27,1,27,2],[27,3,27,4],[27,6,27,7],[28,1,28,2],[28,3,28,4],[28,6,28,7],[29,1,29,2],[29,3,29,4],[29,6,29,7],[30,1,30,2],[30,3,30,4],[30,6,30,7],[31,1,31,2],[31,3,31,4],[31,6,31,7],[32,1,32,2],[32,3,32,4],[32,6,32,7],[33,1,33,2],[33,3,33,4],[33,6,33,7],[34,1,34,2],[34,3,34,4],[34,6,34,7],[35,1,35,2],[35,3,35,4],[35,6,35,7],[36,1,36,2],[36,3,36,4],[36,6,36,7],[37,1,37,2],[37,3,37,4],[37,6,37,7],[38,1,38,2],[38,3,38,4],[38,6,38,7],[39,1,39,2],[39,3,39,4],[39,6,39,7],[40,1,40,2],[40,3,40,4],[40,6,40,7],[41,0,41,7],[43,2,43,8]]}
["附录G 不可竞争项目清单与计价表"]
["工程名称：5、6、11、12、13号",{"$nulls":3},"标段：",null,null,"第1页 共1页"]
["序号","项目编码",null,"项目名称",null,"计算基数","费率（%）",null,"金额（元）"]
["1","ZF-01",null,"环境保护费",null,null,"2.600"]
["2","ZF-02",null,"文明施工费",null,null,"4.500"]
["3","ZF-03",null,"安全施工费",null,null,"3.100"]
["4","ZF-04",null,"临时设施费",null,null,"5.800"]
["5","ZF-05",null,"环境保护税",null,null,""]
{"$rows_empty":33}
["合   计",{"$nulls":7},""]
[]
[null,null,"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"4.1 E.1 分部分项工程量清单计价表(所有标题)","index":7,"n_rows":97,"n_cols":14,"rows_kept":97,"merged":[[0,0,0,13],[1,0,1,5],[1,6,1,10],[1,11,1,13],[2,0,4,0],[2,1,4,1],[2,2,4,3],[2,4,4,4],[2,5,4,6],[2,7,4,7],[2,8,2,13],[3,8,4,8],[3,9,4,9],[3,10,3,13],[4,10,4,11],[5,2,5,4],[5,5,5,6],[5,10,5,11],[6,2,6,3],[6,5,6,6],[6,10,6,11],[7,2,7,3],[7,5,7,6],[7,10,7,11],[8,2,8,3],[8,5,8,6],[8,10,8,11],[9,2,9,3],[9,5,9,6],[9,10,9,11],[10,2,10,3],[10,5,10,6],[10,10,10,11],[11,2,11,3],[11,5,11,6],[11,10,11,11],[12,2,12,3],[12,5,12,6],[12,10,12,11],[13,2,13,4],[13,5,13,6],[13,10,13,11],[14,2,14,4],[14,5,14,6],[14,10,14,11],[15,2,15,3],[15,5,15,6],[15,10,15,11],[16,2,16,3],[16,5,16,6],[16,10,16,11],[17,2,17,3],[17,5,17,6],[17,10,17,11],[18,2,18,3],[18,5,18,6],[18,10,18,11],[19,2,19,3],[19,5,19,6],[19,10,19,11],[20,2,20,3],[20,5,20,6],[20,10,20,11],[21,2,21,3],[21,5,21,6],[21,10,21,11],[22,2,22,3],[22,5,22,6],[22,10,22,11],[23,2,23,3],[23,5,23,6],[23,10,23,11],[24,2,24,3],[24,5,24,6],[24,10,24,11],[25,2,25,4],[25,5,25,6],[25,10,25,11],[26,2,26,4],[26,5,26,6],[26,10,26,11],[27,2,27,3],[27,5,27,6],[27,10,27,11],[28,2,28,3],[28,5,28,6],[28,10,28,11],[29,2,29,3],[29,5,29,6],[29,10,29,11],[30,2,30,3],[30,5,30,6],[30,10,30,11],[31,0,31,13],[32,3,32,13],[33,0,33,13],[34,0,34,5],[34,6,34,10],[34,11,34,13],[35,0,37,0],[35,1,37,1],[35,2,37,3],[35,4,37,4],[35,5,37,6],[35,7,37,7],[35,8,35,13],[36,8,37,8],[36,9,37,9],[36,10,36,13],[37,10,37,11],[38,2,38,3],[38,5,38,6],[38,10,38,11],[39,2,39,3],[39,5,39,6],[39,10,39,11],[40,2,40,3],[40,5,40,6],[40,10,40,11],[41,2,41,3],[41,5,41,6],[41,10,41,11],[42,2,42,3],[42,5,42,6],[42,10,42,11],[43,2,43,3],[43,5,43,6],[43,10,43,11],[44,2,44,3],[44,5,44,6],[44,10,44,11],[45,2,45,3],[45,5,45,6],[45,10,45,11],[46,2,46,3],[46,5,46,6],[46,10,46,11],[47,2,47,3],[47,5,47,6],[47,10,47,11],[48,2,48,3],[48,5,48,6],[48,10,48,11],[49,2,49,3],[49,5,49,6],[49,10,49,11],[50,2,50,3],[50,5,50,6],[50,10,50,11],[51,2,51,3],[51,5,51,6],[51,10,51,11],[52,2,52,3],[52,5,52,6],[52,10,52,11],[53,2,53,3],[53,5,53,6],[53,10,53,11],[54,2,54,3],[54,5,54,6],[54,10,54,11],[55,2,55,4],[55,5,55,6],[55,10,55,11],[56,2,56,4],[56,5,56,6],[56,10,56,11],[57,2,57,3],[57,5,57,6],[57,10,57,11],[58,2,58,3],[58,5,58,6],[58,10,58,11],[59,2,59,3],[59,5,59,6],[59,10,59,11],[60,2,60,3],[60,5,60,6],[60,10,60,11],[61,0,61,13],[62,3,62,13],[63,0,63,13],[64,0,64,5],[64,6,64,10],[64,11,64,13],[65,0,67,0],[65,1,67,1],[65,2,67,3],[65,4,67,4],[65,5,67,6],[65,7,67,7],[65,8,65,13],[66,8,67,8],[66,9,67,9],[66,10,66,13],[67,10,67,11],[68,2,68,3],[68,5,68,6],[68,10,68,11],[69,2,69,3],[69,5,69,6],[69,10,69,11],[70,2,70,3],[70,5,70,6],[70,10,70,11],[71,2,71,3],[71,5,71,6],[71,10,71,11],[72,2,72,3],[72,5,72,6],[72,10,72,11],[73,2,73,3],[73,5,73,6],[73,10,73,11],[74,2,74,3],[74,5,74,6],[74,10,74,11],[75,2,75,3],[75,5,75,6],[75,10,75,11],[76,2,76,3],[76,5,76,6],[76,10,76,11],[77,2,77,4],[77,5,77,6],[77,10,77,11],[78,2,78,4],[78,5,78,6],[78,10,78,11],[79,2,79,3],[79,5,79,6],[79,10,79,11],[80,2,80,3],[80,5,80,6],[80,10,80,11],[81,2,81,4],[81,5,81,6],[81,10,81,11],[82,2,82,3],[82,5,82,6],[82,10,82,11],[83,2,83,3],[83,5,83,6],[83,10,83,11],[84,2,84,3],[84,5,84,6],[84,10,84,11],[85,2,85,3],[85,5,85,6],[85,10,85,11],[86,2,86,3],[86,5,86,6],[86,10,86,11],[87,2,87,3],[87,5,87,6],[87,10,87,11],[88,2,88,3],[88,5,88,6],[88,10,88,11],[89,2,89,3],[89,5,89,6],[89,10,89,11],[90,2,90,3],[90,5,90,6],[90,10,90,11],[91,2,91,3],[91,5,91,6],[91,10,91,11],[92,2,92,3],[92,5,92,6],[92,10,92,11],[93,2,93,3],[93,5,93,6],[93,10,93,11],[94,0,94,13],[96,3,96,13]]}
["E.1 分部分项工程量清单计价表"]
["工程名称：7~10号",{"$nulls":5},"标段：",{"$nulls":4},"第1页 共3页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
[null,"7号",{"$nulls":5},""]
["1","011615001001","开门洞",null,"1、现有墙体拆除","个",null,"2.000"]
["2","011610001002","门拆除",null,"1、成套门","个",null,"2.000"]
["3","010402001003","封门洞",null,"1、加气块及双面粉刷","个",null,"2.000"]
["4","ZB010101001003","封门洞双面局部腻子及乳胶漆处理",null,null,"项",null,"2.000"]
["5","011101001001","地台拆除地砖及粉刷",null,"1、人工及辅材","m2",null,"3.600"]
["6","011406001005","卫生间区域墙面乳胶漆打磨",null,"1、人工及下运","m2",null,"9.540"]
["7","010904001002","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"14.500"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"8号",{"$nulls":5},""]
["8","011614003001","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["9","011406003001","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["10","011406001001","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["11","011406003002","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["12","041001006002","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["13","011606003001","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"30.300"]
["14","ZB010101001001","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["15","ZB010101001002","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"8.500"]
["16","010402001001","新建墙体及双面粉刷（卫生间到顶）",null,"1、加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"18.800"]
["17","010402001002","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷","m2",null,"25.000"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"9号",{"$nulls":5},""]
["18","011601001001","墙体拆除",null,"1、现有墙体拆除","m2",null,"9.800"]
["19","011606003002","石膏板吊顶拆除",null,"1、石膏板拆除及下运","m2",null,"33.000"]
[]
[]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：7~10号",{"$nulls":5},"标段：",{"$nulls":4},"第2页 共3页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["20","ZB010101001004","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
["21","041001006003","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["22","011614002004","柜子拆除",null,"1、人工及下运","个",null,"1.000"]
["23","011614002005","浴室柜子拆除（1.94米长）",null,"1、人工及下运","个",null,"1.000"]
["24","011606001002","楼地面龙骨及饰面拆除",null,"1、地台拆除，含人工及下运","m2",null,"5.200"]
["25","011101001003","水泥砂浆楼地面",null,"1、地台拆除后粉刷（高度20公分)","m2",null,"9.000"]
["26","011606003003","天棚面龙骨及饰面拆除",null,"1、集成吊顶拆除，含人工及下运","m2",null,"5.200"]
["27","011614003004","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["28","011406003007","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["29","011406001012","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["30","011406003008","阳台门拆除后墙面腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["31","011406001013","阳台门拆除后墙面乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["32","011601001003","背景墙拆除",null,"1、现有墙体拆除","m2",null,"8.500"]
["33","011406001011","背景墙拆除后墙面腻子及乳胶漆处理",null,"1、人工及主材","m2",null,"8.500"]
["34","ZB010101001006","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"8.500"]
["35","010402001006","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"18.800"]
["36","010402001007","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"25.000"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"10号",{"$nulls":5},""]
["37","ZB010101001007","油烟机拆除",null,"1、人工及下运","项",null,"1.000"]
["38","011615001002","开门洞",null,null,"个",null,"1.000"]
["39","011606003004","天棚面龙骨及饰面拆除",null,"1、集成吊顶拆除，含人工及下运","m2",null,"22.500"]
["40","ZB010101001008","石膏板吊顶拆除后线路调整",null,"1、整理线路 固定在顶上或者就近剪断包住","项",null,"1.000"]
[]
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]
["E.1 分部分项工程量清单计价表"]
["工程名称：7~10号",{"$nulls":5},"标段：",{"$nulls":4},"第3页 共3页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["41","011614003005","窗台下石膏板及窗台石拆除",null,"1、人工及下运","项",null,"1.000"]
["42","011406003009","窗台下拆除后腻子修补",null,"1、人工及辅材","项",null,"1.000"]
["43","011406001014","窗台下拆除后乳胶漆",null,"1、人工及辅材","项",null,"1.000"]
["44","041001006001","包管拆除",null,"1、人工及下运","个",null,"4.000"]
["45","010201001001","卫生间地面抬高",null,"1、水泥黄沙加气块及豆石20公分高","m2",null,"2.770"]
["46","010904001001","新建卫生间墙地面防水",null,"1、东方雨虹，地面全刷，墙面1.8米高（门洞减半）","m2",null,"18.500"]
["47","ZB010101001009","新建墙体地面处开槽",null,"1、切割机切槽","m",null,"3.500"]
["48","010402001008","新建墙体及双面粉刷（卫生间到顶）",null,"1、10公分加气块隔墙，厨房隔墙预留门洞及双面水泥沙粉刷","m2",null,"7.200"]
["49","010402001009","新建砖墙体及双面局部腻子及乳胶漆处理",null,"1、厨房及卫生间内部水泥沙粉刷 外侧石膏腻子乳胶漆及人工","m2",null,"14.400"]
[null,null,"分部小计",{"$nulls":4},""]
[null,"其他",{"$nulls":5},""]
["50","WB011614004001","建筑垃圾外运",null,"1、1项约50平方约4000元清运费","项",null,"3.000"]
["51","ZB010101001011","卫生间水电改造",null,"1、人工及辅材（1.马桶下水及进水2.浴室柜进水及下水 3.淋浴进水及下水）","间",null,"2.000"]
[null,null,"分部小计",{"$nulls":4},""]
{"$rows_empty":14}
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"4.2 附录F 措施项目清单计价表","index":8,"n_rows":44,"n_cols":9,"rows_kept":44,"merged":[[0,0,0,8],[1,0,1,3],[1,4,1,6],[1,7,1,8],[2,1,2,2],[2,3,2,4],[2,6,2,7],[3,1,3,2],[3,3,3,4],[3,6,3,7],[4,1,4,2],[4,3,4,4],[4,6,4,7],[5,1,5,2],[5,3,5,4],[5,6,5,7],[6,1,6,2],[6,3,6,4],[6,6,6,7],[7,1,7,2],[7,3,7,4],[7,6,7,7],[8,1,8,2],[8,3,8,4],[8,6,8,7],[9,1,9,2],[9,3,9,4],[9,6,9,7],[10,1,10,2],[10,3,10,4],[10,6,10,7],[11,1,11,2],[11,3,11,4],[11,6,11,7],[12,1,12,2],[12,3,12,4],[12,6,12,7],[13,1,13,2],[13,3,13,4],[13,6,13,7],[14,1,14,2],[14,3,14,4],[14,6,14,7],[15,1,15,2],[15,3,15,4],[15,6,15,7],[16,1,16,2],[16,3,16,4],[16,6,16,7],[17,1,17,2],[17,3,17,4],[17,6,17,7],[18,1,18,2],[18,3,18,4],[18,6,18,7],[19,1,19,2],[19,3,19,4],[19,6,19,7],[20,1,20,2],[20,3,20,4],[20,6,20,7],[21,1,21,2],[21,3,21,4],[21,6,21,7],[22,1,22,2],[22,3,22,4],[22,6,22,7],[23,1,23,2],[23,3,23,4],[23,6,23,7],[24,1,24,2],[24,3,24,4],[24,6,24,7],[25,1,25,2],[25,3,25,4],[25,6,25,7],[26,1,26,2],[26,3,26,4],[26,6,26,7],[27,1,27,2],[27,3,27,4],[27,6,27,7],[28,1,28,2],[28,3,28,4],[28,6,28,7],[29,1,29,2],[29,3,29,4],[29,6,29,7],[30,1,30,2],[30,3,30,4],[30,6,30,7],[31,1,31,2],[31,3,31,4],[31,6,31,7],[32,1,32,2],[32,3,32,4],[32,6,32,7],[33,1,33,2],[33,3,33,4],[33,6,33,7],[34,1,34,2],[34,3,34,4],[34,6,34,7],[35,1,35,2],[35,3,35,4],[35,6,35,7],[36,1,36,2],[36,3,36,4],[36,6,36,7],[37,1,37,2],[37,3,37,4],[37,6,37,7],[38,1,38,2],[38,3,38,4],[38,6,38,7],[39,1,39,2],[39,3,39,4],[39,6,39,7],[40,1,40,2],[40,3,40,4],[40,6,40,7],[41,0,41,7],[43,2,43,8]]}
["附录F 措施项目清单与计价表"]
["工程名称：7~10号",{"$nulls":3},"标段：",null,null,"第1页 共1页"]
["序号","项目编码",null,"项目名称",null,"计算基础","费率（%）",null,"金额（元）"]
["1","ZC-01",null,"夜间施工增加费",null,null,"0.500"]
["2","ZC-02",null,"二次搬运费",null,null,"1.200"]
["3","ZC-03",null,"冬雨季施工增加费",null,null,"0.700"]
["4","ZC-04",null,"已完工程及设备保护费",null,null,"0.500"]
["5","ZC-05",null,"工程定位复测费",null,null,"0.800"]
["6","ZC-06",null,"非夜间施工照明费",null,null,"0.400"]
["7","ZC-07",null,"临时保护设施费",null,null,"0.100"]
["8","ZC-08",null,"赶工措施费",null,null,"2.100"]
{"$rows_empty":30}
["合   计",{"$nulls":7},""]
[]
[null,null,"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"4.3 附录G 不可竞争项目清单与计价表","index":9,"n_rows":44,"n_cols":9,"rows_kept":44,"merged":[[0,0,0,8],[1,0,1,3],[1,4,1,6],[1,7,1,8],[2,1,2,2],[2,3,2,4],[2,6,2,7],[3,1,3,2],[3,3,3,4],[3,6,3,7],[4,1,4,2],[4,3,4,4],[4,6,4,7],[5,1,5,2],[5,3,5,4],[5,6,5,7],[6,1,6,2],[6,3,6,4],[6,6,6,7],[7,1,7,2],[7,3,7,4],[7,6,7,7],[8,1,8,2],[8,3,8,4],[8,6,8,7],[9,1,9,2],[9,3,9,4],[9,6,9,7],[10,1,10,2],[10,3,10,4],[10,6,10,7],[11,1,11,2],[11,3,11,4],[11,6,11,7],[12,1,12,2],[12,3,12,4],[12,6,12,7],[13,1,13,2],[13,3,13,4],[13,6,13,7],[14,1,14,2],[14,3,14,4],[14,6,14,7],[15,1,15,2],[15,3,15,4],[15,6,15,7],[16,1,16,2],[16,3,16,4],[16,6,16,7],[17,1,17,2],[17,3,17,4],[17,6,17,7],[18,1,18,2],[18,3,18,4],[18,6,18,7],[19,1,19,2],[19,3,19,4],[19,6,19,7],[20,1,20,2],[20,3,20,4],[20,6,20,7],[21,1,21,2],[21,3,21,4],[21,6,21,7],[22,1,22,2],[22,3,22,4],[22,6,22,7],[23,1,23,2],[23,3,23,4],[23,6,23,7],[24,1,24,2],[24,3,24,4],[24,6,24,7],[25,1,25,2],[25,3,25,4],[25,6,25,7],[26,1,26,2],[26,3,26,4],[26,6,26,7],[27,1,27,2],[27,3,27,4],[27,6,27,7],[28,1,28,2],[28,3,28,4],[28,6,28,7],[29,1,29,2],[29,3,29,4],[29,6,29,7],[30,1,30,2],[30,3,30,4],[30,6,30,7],[31,1,31,2],[31,3,31,4],[31,6,31,7],[32,1,32,2],[32,3,32,4],[32,6,32,7],[33,1,33,2],[33,3,33,4],[33,6,33,7],[34,1,34,2],[34,3,34,4],[34,6,34,7],[35,1,35,2],[35,3,35,4],[35,6,35,7],[36,1,36,2],[36,3,36,4],[36,6,36,7],[37,1,37,2],[37,3,37,4],[37,6,37,7],[38,1,38,2],[38,3,38,4],[38,6,38,7],[39,1,39,2],[39,3,39,4],[39,6,39,7],[40,1,40,2],[40,3,40,4],[40,6,40,7],[41,0,41,7],[43,2,43,8]]}
["附录G 不可竞争项目清单与计价表"]
["工程名称：7~10号",{"$nulls":3},"标段：",null,null,"第1页 共1页"]
["序号","项目编码",null,"项目名称",null,"计算基数","费率（%）",null,"金额（元）"]
["1","ZF-01",null,"环境保护费",null,null,"2.600"]
["2","ZF-02",null,"文明施工费",null,null,"4.500"]
["3","ZF-03",null,"安全施工费",null,null,"3.100"]
["4","ZF-04",null,"临时设施费",null,null,"5.800"]
["5","ZF-05",null,"环境保护税",null,null,""]
{"$rows_empty":33}
["合   计",{"$nulls":7},""]
[]
[null,null,"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"5.1 E.1 分部分项工程量清单计价表(所有标题)","index":10,"n_rows":37,"n_cols":14,"rows_kept":37,"merged":[[0,0,0,13],[1,0,1,5],[1,6,1,10],[1,11,1,13],[2,0,4,0],[2,1,4,1],[2,2,4,3],[2,4,4,4],[2,5,4,6],[2,7,4,7],[2,8,2,13],[3,8,4,8],[3,9,4,9],[3,10,3,13],[4,10,4,11],[5,2,5,3],[5,5,5,6],[5,10,5,11],[6,2,6,3],[6,5,6,6],[6,10,6,11],[7,2,7,3],[7,5,7,6],[7,10,7,11],[8,2,8,3],[8,5,8,6],[8,10,8,11],[9,2,9,3],[9,5,9,6],[9,10,9,11],[10,2,10,3],[10,5,10,6],[10,10,10,11],[11,2,11,3],[11,5,11,6],[11,10,11,11],[12,2,12,3],[12,5,12,6],[12,10,12,11],[13,2,13,3],[13,5,13,6],[13,10,13,11],[14,2,14,3],[14,5,14,6],[14,10,14,11],[15,2,15,3],[15,5,15,6],[15,10,15,11],[16,2,16,3],[16,5,16,6],[16,10,16,11],[17,2,17,3],[17,5,17,6],[17,10,17,11],[18,2,18,3],[18,5,18,6],[18,10,18,11],[19,2,19,3],[19,5,19,6],[19,10,19,11],[20,2,20,3],[20,5,20,6],[20,10,20,11],[21,2,21,3],[21,5,21,6],[21,10,21,11],[22,2,22,3],[22,5,22,6],[22,10,22,11],[23,2,23,3],[23,5,23,6],[23,10,23,11],[24,2,24,3],[24,5,24,6],[24,10,24,11],[25,2,25,3],[25,5,25,6],[25,10,25,11],[26,2,26,3],[26,5,26,6],[26,10,26,11],[27,2,27,3],[27,5,27,6],[27,10,27,11],[28,2,28,3],[28,5,28,6],[28,10,28,11],[29,2,29,3],[29,5,29,6],[29,10,29,11],[30,2,30,3],[30,5,30,6],[30,10,30,11],[31,2,31,3],[31,5,31,6],[31,10,31,11],[32,2,32,3],[32,5,32,6],[32,10,32,11],[33,2,33,3],[33,5,33,6],[33,10,33,11],[34,2,34,3],[34,5,34,6],[34,10,34,11],[35,0,35,13],[36,3,36,13]]}
["E.1 分部分项工程量清单计价表"]
["工程名称：922室修补项目",{"$nulls":5},"标段：",{"$nulls":4},"第1页 共1页"]
["序号","项目编码","项目名称",null,"项目特征描述","计量\n单位",null,"工程量","金额（元）"]
[{"$nulls":8},"综合单价","合价","其中"]
[{"$nulls":10},"定额\n人工费",null,"定额\n机械费","暂估价"]
["1","011615001001","1022阳台地面铲除",null,"人工及下运","项",null,"1.000"]
["2","011615001002","1022阳台地面水泥沙粉平",null,"人工及下运","项",null,"1.000"]
["3","011615001003","1022阳台墙面打磨至50公分高",null,"人工及下运","项",null,"1.000"]
["4","011615001004","1022阳台墙面地面防水",null,"东方雨虹，地面全刷，墙面0.5米高","项",null,"1.000"]
["5","011615001005","1022阳台墙面地面防水后粉刷",null,"东方雨虹，地面全刷，墙面0.5米高","项",null,"1.000"]
["6","011615001006","922室阳台顶面及墙面铲除",null,"人工","项",null,"1.000"]
["7","011615001007","922室阳台顶面腻子修补及乳胶漆",null,"基层处理 腻子两遍打磨后两遍面漆","项",null,"1.000"]
["8","011615001008","卫生间顶面拆除",null,"人工及下运","项",null,"1.000"]
["9","011615001009","卫生间顶面集成吊顶及灯更换300*300",null,"铝扣板，边条，龙骨，吊筋，人工，300*300方灯及换气扇","项",null,"1.000"]
{"$rows_empty":22}
[{"$nulls":3},"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"5.2 附录F 措施项目清单计价表","index":11,"n_rows":44,"n_cols":9,"rows_kept":44,"merged":[[0,0,0,8],[1,0,1,3],[1,4,1,6],[1,7,1,8],[2,1,2,2],[2,3,2,4],[2,6,2,7],[3,1,3,2],[3,3,3,4],[3,6,3,7],[4,1,4,2],[4,3,4,4],[4,6,4,7],[5,1,5,2],[5,3,5,4],[5,6,5,7],[6,1,6,2],[6,3,6,4],[6,6,6,7],[7,1,7,2],[7,3,7,4],[7,6,7,7],[8,1,8,2],[8,3,8,4],[8,6,8,7],[9,1,9,2],[9,3,9,4],[9,6,9,7],[10,1,10,2],[10,3,10,4],[10,6,10,7],[11,1,11,2],[11,3,11,4],[11,6,11,7],[12,1,12,2],[12,3,12,4],[12,6,12,7],[13,1,13,2],[13,3,13,4],[13,6,13,7],[14,1,14,2],[14,3,14,4],[14,6,14,7],[15,1,15,2],[15,3,15,4],[15,6,15,7],[16,1,16,2],[16,3,16,4],[16,6,16,7],[17,1,17,2],[17,3,17,4],[17,6,17,7],[18,1,18,2],[18,3,18,4],[18,6,18,7],[19,1,19,2],[19,3,19,4],[19,6,19,7],[20,1,20,2],[20,3,20,4],[20,6,20,7],[21,1,21,2],[21,3,21,4],[21,6,21,7],[22,1,22,2],[22,3,22,4],[22,6,22,7],[23,1,23,2],[23,3,23,4],[23,6,23,7],[24,1,24,2],[24,3,24,4],[24,6,24,7],[25,1,25,2],[25,3,25,4],[25,6,25,7],[26,1,26,2],[26,3,26,4],[26,6,26,7],[27,1,27,2],[27,3,27,4],[27,6,27,7],[28,1,28,2],[28,3,28,4],[28,6,28,7],[29,1,29,2],[29,3,29,4],[29,6,29,7],[30,1,30,2],[30,3,30,4],[30,6,30,7],[31,1,31,2],[31,3,31,4],[31,6,31,7],[32,1,32,2],[32,3,32,4],[32,6,32,7],[33,1,33,2],[33,3,33,4],[33,6,33,7],[34,1,34,2],[34,3,34,4],[34,6,34,7],[35,1,35,2],[35,3,35,4],[35,6,35,7],[36,1,36,2],[36,3,36,4],[36,6,36,7],[37,1,37,2],[37,3,37,4],[37,6,37,7],[38,1,38,2],[38,3,38,4],[38,6,38,7],[39,1,39,2],[39,3,39,4],[39,6,39,7],[40,1,40,2],[40,3,40,4],[40,6,40,7],[41,0,41,7],[43,2,43,8]]}
["附录F 措施项目清单与计价表"]
["工程名称：922室修补项目",{"$nulls":3},"标段：",null,null,"第1页 共1页"]
["序号","项目编码",null,"项目名称",null,"计算基础","费率（%）",null,"金额（元）"]
["1","JC-01",null,"夜间施工增加费",null,null,"0.500"]
["2","JC-02",null,"二次搬运费",null,null,"1.000"]
["3","JC-03",null,"冬雨季施工增加费",null,null,"0.800"]
["4","JC-04",null,"已完工程及设备保护费",null,null,"0.100"]
["5","JC-05",null,"工程定位复测费",null,null,"1.000"]
["6","JC-06",null,"非夜间施工照明费",null,null,"0.400"]
["7","JC-07",null,"临时保护设施费",null,null,"0.200"]
["8","JC-08",null,"赶工措施费",null,null,"2.200"]
{"$rows_empty":30}
["合   计",{"$nulls":7},""]
[]
[null,null,"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]

{"sheet":"5.3 附录G 不可竞争项目清单与计价表","index":12,"n_rows":44,"n_cols":9,"rows_kept":44,"merged":[[0,0,0,8],[1,0,1,3],[1,4,1,6],[1,7,1,8],[2,1,2,2],[2,3,2,4],[2,6,2,7],[3,1,3,2],[3,3,3,4],[3,6,3,7],[4,1,4,2],[4,3,4,4],[4,6,4,7],[5,1,5,2],[5,3,5,4],[5,6,5,7],[6,1,6,2],[6,3,6,4],[6,6,6,7],[7,1,7,2],[7,3,7,4],[7,6,7,7],[8,1,8,2],[8,3,8,4],[8,6,8,7],[9,1,9,2],[9,3,9,4],[9,6,9,7],[10,1,10,2],[10,3,10,4],[10,6,10,7],[11,1,11,2],[11,3,11,4],[11,6,11,7],[12,1,12,2],[12,3,12,4],[12,6,12,7],[13,1,13,2],[13,3,13,4],[13,6,13,7],[14,1,14,2],[14,3,14,4],[14,6,14,7],[15,1,15,2],[15,3,15,4],[15,6,15,7],[16,1,16,2],[16,3,16,4],[16,6,16,7],[17,1,17,2],[17,3,17,4],[17,6,17,7],[18,1,18,2],[18,3,18,4],[18,6,18,7],[19,1,19,2],[19,3,19,4],[19,6,19,7],[20,1,20,2],[20,3,20,4],[20,6,20,7],[21,1,21,2],[21,3,21,4],[21,6,21,7],[22,1,22,2],[22,3,22,4],[22,6,22,7],[23,1,23,2],[23,3,23,4],[23,6,23,7],[24,1,24,2],[24,3,24,4],[24,6,24,7],[25,1,25,2],[25,3,25,4],[25,6,25,7],[26,1,26,2],[26,3,26,4],[26,6,26,7],[27,1,27,2],[27,3,27,4],[27,6,27,7],[28,1,28,2],[28,3,28,4],[28,6,28,7],[29,1,29,2],[29,3,29,4],[29,6,29,7],[30,1,30,2],[30,3,30,4],[30,6,30,7],[31,1,31,2],[31,3,31,4],[31,6,31,7],[32,1,32,2],[32,3,32,4],[32,6,32,7],[33,1,33,2],[33,3,33,4],[33,6,33,7],[34,1,34,2],[34,3,34,4],[34,6,34,7],[35,1,35,2],[35,3,35,4],[35,6,35,7],[36,1,36,2],[36,3,36,4],[36,6,36,7],[37,1,37,2],[37,3,37,4],[37,6,37,7],[38,1,38,2],[38,3,38,4],[38,6,38,7],[39,1,39,2],[39,3,39,4],[39,6,39,7],[40,1,40,2],[40,3,40,4],[40,6,40,7],[41,0,41,7],[43,2,43,8]]}
["附录G 不可竞争项目清单与计价表"]
["工程名称：922室修补项目",{"$nulls":3},"标段：",null,null,"第1页 共1页"]
["序号","项目编码",null,"项目名称",null,"计算基数","费率（%）",null,"金额（元）"]
["1","JF-01",null,"环境保护费",null,null,"3.280"]
["2","JF-02",null,"文明施工费",null,null,"5.120"]
["3","JF-03",null,"安全施工费",null,null,"4.130"]
["4","JF-04",null,"临时设施费",null,null,"8.100"]
["5","JF-05",null,"环境保护税",null,null,""]
{"$rows_empty":33}
["合   计",{"$nulls":7},""]
[]
[null,null,"测评合格编号:2021JS-02【新点造价软件V10.0安徽版】"]